## Scope (hidden)
Inital Risk Review Date
Location:
Business Unit:
Title :
Project Name & Category
Scope:
Reviewer:
Approver:
Custodian:
| Attendees List |  |  |  |  | Date 2
Date 1
No. | Name | Company | Title |  | Tel. | E-mail
1 |  |  |  | plastow
2 |  |  |  | Kenneth Gray
3 |  |  |  | Matthew Vick
4 |  |  |  | Mohamed Atef
5 |  |  |  | Stan Ralph
6 |  |  |  | Andrea Hughes
7 |  |  |  | Barry Valentine
8 |  |  |  | Rob Munger
9 |  |  |  | Jeff Smith
10 |  |  |  | Kevin Rothery
11 |  |  |  | Carlos Henriques
12 |  |  |  | Richard Gall
13 |  |  |  | Mauricio Useche
14 |  |  |  | Bob Hamilton
15 |  |  |  | John Keyte
16 |  |  |  | Ahmed Fouad
17 |  |  |  | Bob Johansen
18 |  |  |  | Martin Pritchett
19 |  |  |  | Matthew Law
20 |  |  |  | George Stead
21 |  |  |  | George Waugh
22 |  |  |  | Jackson dos Santos
23 |  |  |  | Miguel Campos Dias
24 |  |  |  | Kelly Rives
25 |  |  |  | Justin Bullard
26 |  |  |  | Dave Jenner
27 |  |  |  | Mohamed Shawky
28 |  |  |  | Mohammed Issa
29 |  |  |  | Paul Martyniak
30 |  |  |  | Andrew Humphrey
31 |  |  |  | Jose C Gabriel
32 |  |  |  | Napier
33 |  |  |  | O'Leary
34
35
36
37

## Risk Register (Generic) (hidden)
Risk Register ID: | [14 empty] | Probability |  | Impact
[15 empty] | Nil | 0 | Very Low | 0.1
Project: |  |  |  | Business Unit(s): |  |  |  | Location(s): | [6 empty] | Very Low | 0.1 | Low | 0.3
[15 empty] | Low | 0.3 | Moderate | 0.5
Risk # | Risk Category | Threat or Opportunity | Risk Description (Note 1) | Unmitigated Risk |  |  | Risk Response |  |  | Resultant Risk |  |  | Contingency Plan Required? | Contingency Plan | Medium | 0.5 | High | 0.7
|  |  |  | Probability | Impact | Risk Score | Owner | Plan | Status | Probability | Impact | Risk Score |  |  | High | 0.7 | Very High | 0.9
[6 empty] | 0 | [5 empty] | 0 |  |  | Very High | 0.9
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0
[6 empty] | 0 | [5 empty] | 0

## Cover
Risk Register & RAM for AI Systems
Document Number | [Associated Number]
Revision | A

## Revisions
Document Owner
AI Governance
Revision History
Revision | Prepared by | Reviewed by | Approved by | Date Approved
A | Clint Coker | Sean McCall | Maria O'Neill | <<MM/DD/YYYY>>
Revision Details
Revision | Change Details
A
Purpose

## AI Risk Subcats
AI Risk Subcategories
Name | Description
Access & Endpoint Risk | Risk that uncontrolled AI endpoints, tools, or interfaces enable data leakage, unauthorized use, or inconsistent controls. Includes lack of centralized AI access, routing, and policy enforcement mechanisms.
Audit & Assurance Risk | Risk that AI systems cannot be adequately audited due to missing documentation, metadata, logs, or decision traceability. Impairs internal assurance and readiness for external audit or regulator inquiry.
Data Risk | Risk arising from poor data quality, inappropriate data use, oversharing, or exposure of sensitive, proprietary, or regulated data. Includes lineage gaps, consent violations, and inadequate data classification or access controls.
Ethical Risk | Risk that AI systems produce unfair, biased, opaque, or non‑explainable outcomes that conflict with Responsible AI principles. Includes discrimination, lack of transparency, and erosion of human accountability.
Human Oversight & Misuse Risk | Risk that humans over‑rely on AI outputs, misuse tools outside approved scope, or bypass controls. Includes automation bias, insufficient [human] training, and lack of clearly defined human‑in‑the‑loop responsibilities.
Legal & Compliance Risk | Risk that AI use violates laws, regulations, contracts, export controls, or internal standards across jurisdictions. Includes privacy, IP, licensing, government-use restrictions, and misalignment with ISO, IMS, or regulatory obligations.
Model Risk | Risk that an AI model is inaccurate, unstable, poorly validated, or unsuitable for its intended use. Includes training data quality issues, concept drift, overfitting, and lack of documented assumptions or limitations.
Operational Risk [Operation of the AI Product] | Risk that AI systems fail to perform reliably in production due to inadequate monitoring, change (control) management, incident response, or dependency management. Includes weak ownership, unclear escalation paths, and lack of lifecycle controls.
Regulatory Change Risk | Risk that (1) AI technology evolution outpaces existing regulatory guidance and enterprise governance capabilities, and (2) that AI regulations outpace the enterprise’s controls, processes, and tooling. This misalignment can create compliance gaps, inconsistent deployment, delayed adoption, or forced rework. Mitigate through continuous regulatory horizon scanning, governance‑by‑design, adaptable control frameworks, and traceable impact assessments that evolve with both technology and regulation.
Reputational Risk | Risk that AI failures, misuse, or perceived irresponsibility erode trust with customers, regulators, employees, or partners. Often amplified by public incidents, lack of transparency, or poor incident response.
Safety & Security Risk | Risk that AI contributes to physical harm, unsafe operational decisions, cyber compromise, or data breaches. Includes model exploitation, prompt injection, insecure integrations, and unsafe human‑AI interaction in operational contexts.
Third‑Party / Supply Chain Risk | Risk introduced by external AI vendors, models, APIs, or data sources. Includes opaque vendor practices, licensing uncertainty, security weaknesses, and limited audit or exit rights.
Other | Risk that is not defined in this list. Describe in comment column.

## Risk Register
Risk Register for AI Systems | [14 empty] | Date Created / Revised: |  |  |  | Optional Columns
Name: |  |  | Project No.: |  | Project Category: |  | Project Manager: |  |  | Currency: |  | Business Segment: |  |  | *** Mitigated Risk Assessment ***
Risk Processes: |  | *** Identify Risks *** |  |  | *** Risk Assessment (with existing controls) *** |  |  |  |  | *** Plan & Implement Risk Responses *** |  |  |  |  | NOTE: To be completed for Project Category 3 & 4 and in case of an unmitigated risk score that is High.
No. | Risk Type | Risk Description ("Because of X , there is a potential of Y which could result in Z .") | Risk Category | Risk Owner | Unmitigated Cost of Risk | Probability Rating [1-5] | Impact Type | Impact Rating [1-5] | Risk Score [1-25] | Threat Response Strategy | Opportunity Response Strategy | Risk Response Plan & Implementation/Status/Completion Date | Risk Response Plan Cost | . Column1 | Probability Rating [1-5] | Impact Rating [1-5] | Risk Score [1-25] | Mitigated Cost of Risk | AI Sub-category | Use Case | Comments
1 | Threat | Because of search access inheritance across bid records, there is a potential for users to retrieve projects outside their role which could result in client data exposure. | Technical |  |  | 1 | Market Reputation | 4 | 4 | Mitigate |  | Configure role-based access, project permissions, SSO, and periodic access reviews before production use. |  |  | 1 | 1 | 1 |  | Access & Endpoint Risk | Semantic Smart Search
2 | Threat | Because of quote files stored in shared workspaces, there is a potential for extracted vendor pricing to be accessed by non-project users which could result in margin leakage. | Commercial |  |  | 1 | Financial | 4 | 4 | Mitigate |  | Limit workspaces by project team, restrict exports, and review access logs for quote and bid records. |  |  | 1 | 1 | 1 |  | Access & Endpoint Risk | Quote Extraction
3 | Threat | Because of limited logging of AI scope suggestions, there is a potential for teams to lose traceability from recommendation to decision which could result in audit gaps. | Operations |  |  | 3 | Performance | 3 | 9 | Mitigate |  | Require decision logs linking AI outputs, reviewer notes, bid changes, and approval evidence. |  |  | 2 | 2 | 4 |  | Audit & Assurance Risk | Scoping Analysis | Review
4 | Threat | Because of automated quote extraction without version tracking, there is a potential for teams to rely on stale extracted values which could result in bid errors. | Quality |  |  | 3 | Performance | 3 | 9 | Mitigate |  | Require source file version capture, extraction timestamp, reviewer approval, and exception logging for each quote. |  |  | 1 | 3 | 3 |  | Audit & Assurance Risk | Quote Extraction | Review
5 | Threat | Because of inconsistent quote formats and scanned PDFs, there is a potential for line items, exclusions, or prices to be extracted incorrectly which could result in underpriced bids. | Commercial |  |  | 4 | Financial | 5 | 20 | Mitigate |  | Require confidence thresholds, human review, sample testing, and comparison against source documents before bid submission. |  |  | 2 | 4 | 8 |  | Data Risk | Quote Extraction | Review
6 | Threat | Because of bid history containing obsolete suppliers and terms, there is a potential for search results to surface outdated practices which could result in poor bid assumptions. | Quality |  |  | 3 | Performance | 3 | 9 | Mitigate |  | Set retention rules, archive obsolete records, tag lessons learned, and require date filters in search results. Set quotation date categories with price contingency possibilites. |  |  | 2 | 2 | 4 |  | Data Risk | Semantic Smart Search | Review
7 | Threat | Because of past bid data reflecting supplier preferences, there is a potential for scope recommendations to favor repeat vendors which could result in unfair supplier treatment. | Legal |  |  | 2 | Market Reputation | 3 | 6 | Mitigate |  | Review supplier selection criteria, monitor recommendation patterns, and require reviewer justification for vendor shortlists. |  |  | 1 | 2 | 2 |  | Ethical Risk | Scoping Analysis | Review
8 | Threat | Because of uncurated lessons learned, there is a potential for users to reuse comments about suppliers without context which could result in biased supplier evaluation. | Legal |  |  | 2 | Market Reputation | 3 | 6 | Mitigate |  | Govern lessons learned entries, remove unsupported supplier comments, and require evidence for supplier performance notes. |  |  | 2 | 2 | 4 |  | Ethical Risk | Semantic Smart Search
9 | Threat | Because of user reliance on extracted quote fields, there is a potential for reviewers to skip source validation which could result in missed exclusions or pricing errors. | Operations |  |  | 3 | Financial | 4 | 12 | Mitigate |  | Require reviewer attestation, source document checks, and exception review before extracted values enter bid tables. |  |  | 2 | 3 | 6 |  | Human Oversight & Misuse Risk | Quote Extraction | Review
10 | Threat | Because of AI scope prompts used as bid guidance, there is a potential for BID Engineers or Analysts to treat output as approved judgment which could result in scope omissions. The risk occurs when an estimator treats the AI output as a completed review rather than as a starting point for review. | Quality |  |  | 3 | Performance | 4 | 12 | Mitigate |  | Require BID Engineer and Analyst ownership, approval steps, and checklist review for AI-generated scope analysis. Set Training for the Team to learn secure steps to use AI output. |  |  | 2 | 3 | 6 |  | Human Oversight & Misuse Risk | Scoping Analysis | Review
11 | Threat | Because of vendor quotes containing confidentiality terms, there is a potential for extracted content to be stored or shared beyond permitted use which could result in contract violations. | Legal |  |  | 2 | Financial | 2 | 4 | Mitigate |  | Review vendor terms, limit sharing, apply retention rules, and document approved use of quote data. Set Access Permissions to only BID Engineering Team and Commercial. |  |  | 1 | 2 | 2 |  | Legal & Compliance Risk | Quote Extraction
12 | Threat | Because of search across project records with regulated customer data, there is a potential for users to retrieve controlled information which could result in compliance breach. | Legal |  |  | 1 | Market Reputation | 5 | 5 | Mitigate |  | Classify project data, enforce permissions, block restricted content from indexing, and monitor search activity. |  |  | 1 | 4 | 4 |  | Legal & Compliance Risk | Semantic Smart Search
13 | Threat | Because of errors on tables, markups, and handwritten notes, there is a potential for extracted quote values to differ from source files which could result in bid loss. | Technical |  |  | 2 | Financial | 5 | 10 | Mitigate |  | Test extraction with representative quotes, set accuracy thresholds, and route low-confidence fields to human review. Set human review and approval for every quote extraction. |  |  | 1 | 4 | 4 |  | Model Risk | Quote Extraction | Review
14 | Threat | Because of retrieval gaps across specifications and addenda, there is a potential for scope analysis to omit changed requirements which could result in change orders. | Quality |  |  | 1 | Financial | 4 | 4 | Mitigate |  | Index addenda, compare versions, require source citations, and validate scope output against current bid package. Add to scope new requirements. |  |  | 2 | 3 | 6 |  | Model Risk | Scoping Analysis | Review
15 | Threat | Because of weak content governance, there is a potential for users to search duplicate or conflicting bid records which could result in slower decisions. | Operations |  |  | 2 | Schedule | 3 | 6 | Mitigate |  | Define record ownership, naming rules, duplicate handling, and periodic cleanup for bid history. View bid history, sorted by date (newest first). Ability to compare similar bids to check for similarities and differences in scope. |  |  | 2 | 2 | 4 |  | Operational Risk | Semantic Smart Search
16 | Threat | Because of integration failures between SmartBid and estimating tools, there is a potential for extracted quote data to fail transfer which could result in bid delays. | Operations |  |  | 1 | Schedule | 4 | 4 | Mitigate |  | Test integrations, define fallback procedures, monitor sync errors, and assign support owners. |  |  | 1 | 3 | 3 |  | Operational Risk | Quote Extraction
17 | Threat | Because of changing data retention or privacy rules, there is a potential for extracted bid data to remain stored beyond allowed periods which could result in penalties. | Legal |  |  | 1 | Financial | 4 | 4 | Mitigate |  | Review retention rules each year, map stored fields, and automate deletion or archive workflows. |  |  | 1 | 3 | 3 |  | Regulatory Change Risk | Quote Extraction
18 | Threat | Because of changing procurement rules for supplier evaluation, there is a potential for AI-assisted analysis to miss requirements which could result in noncompliant bid records. | Legal |  |  | 1 | Performance | 4 | 4 | Mitigate |  | Review procurement requirements, update scoring criteria, and require compliance review for affected bids. |  |  | 1 | 3 | 3 |  | Regulatory Change Risk | Scoping Analysis | Review
19 | Threat | Because of AI-generated scope errors in client bids, there is a potential for OII to submit incomplete proposals which could result in loss of client trust. | Commercial |  |  | 4 | Market Reputation | 5 | 20 | Mitigate |  | Require scope validation, peer review, and documented approval before proposal release. |  |  | 2 | 4 | 8 |  | Reputational Risk | Scoping Analysis | Review
20 | Threat | Because of search results exposing old disputes or supplier comments, there is a potential for users to share unsupported claims which could result in supplier concerns. | Legal |  |  | 1 | Market Reputation | 4 | 4 | Mitigate |  | Restrict sensitive notes, require evidence tags, and train users on approved supplier communication. |  |  | 1 | 3 | 3 |  | Reputational Risk | Semantic Smart Search
21 | Threat | Because of missed safety requirements in specifications, there is a potential for scope analysis to exclude safety controls which could result in unsafe work planning. | Health & Safety |  |  | 2 | Health and Safety | 5 | 10 | Escalate |  | Require safety review for scope outputs involving field work, lifting, pressure systems, or hazardous tasks. Index previous bids and recommendations so that AI are aware of safety equipment previously included for specific types of services. |  |  | 1 | 4 | 4 |  | Safety & Security Risk | Scoping Analysis | Review
22 | Threat | Because of indexed project files containing security details, there is a potential for users to retrieve site access or system information which could result in security exposure. | Technical |  |  | 1 | Market Reputation | 5 | 5 | Mitigate |  | Exclude security files from indexing, apply labels, and monitor access to sensitive search results. Knowledge Base pages will have a dedicated access permissions. |  |  | 1 | 4 | 4 |  | Safety & Security Risk | Semantic Smart Search
23 | Threat | Because of vendor-hosted AI processing, there is a potential for OII bid documents to be processed by third parties which could result in data exposure. | Technical |  |  | 3 | Market Reputation | 5 | 15 | Transfer |  | Require vendor security review, data processing terms, subprocessor disclosure, encryption, and breach notification commitments. |  |  | 1 | 4 | 4 |  | Third-Party / Supply Chain Risk | Quote Extraction | Review
24 | Threat | Because of reliance on ConstructConnect platform availability, there is a potential for search and bid records to be unavailable which could result in bid delays. | Operations |  |  | 1 | Schedule | 4 | 4 | Transfer |  | Require SLA terms, support commitments, backup exports, and downtime procedures for active bids. |  |  | 1 | 3 | 3 |  | Third-Party / Supply Chain Risk | Semantic Smart Search
25 | Threat | Because of poor user training on AI search limits, there is a potential for users to overtrust retrieved records which could result in weak bid decisions. | Operations |  |  | 3 | Performance | 3 | 9 | Mitigate |  | Train users on search limits, source validation, and when to escalate uncertain results. Add documented review and approval before proposal release. |  |  | 2 | 2 | 4 |  | Other Risk | Semantic Smart Search | Review
26 | Threat | Because of unclear ownership for AI-assisted bid outputs, there is a potential for accountability gaps when errors occur which could result in delayed corrective action. | Operations |  |  | 1 | Schedule | 3 | 3 | Mitigate |  | Assign business owner, reviewer, approver, and escalation path for each AI-assisted bid workflow. |  |  | 1 | 2 | 2 |  | Other Risk | Scoping Analysis | Review
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
[9 empty] | 0 | [7 empty] | 0
Note: Copy existing rows and insert them above this row to expand the Risk Register. | [5 empty] | 4 |  | 5 | 20 | [5 empty] | 2 | 4 | 8
Note on C5: Raphael Costa: Permission Control inside our Sharepoint site and webpart database
Note on C6: Raphael Costa: Permission Control inside our Sharepoint site and webpart database
Note on C7: Raphael Costa: We'll have a log from AI Outputs and changes that we made.
Note on C11: Raphael Costa: The AI ​​will not recommend specific suppliers or costs. Instead, it will assist in drafting the scope of supply list by simply listing the necessary equipment, tools, and resources based only on Oceaneering Datasheets and Catalogs; AI Layer it will not address which supplier or cost price should be used. The Knowledge Base will serve solely to identify equipment and part numbers, where available.
Note on C12: Raphael Costa: The AI ​​will not recommend specific suppliers or costs. Instead, it will assist in drafting the scope of supply list by simply listing the necessary equipment, tools, and resources based only on Oceaneering Datasheets and Catalogs; AI Layer it will not address which supplier or cost price should be used. The Knowledge Base will serve solely to identify equipment and part numbers, where available.
Note on C15: Raphael Costa: Our System has permissions access and Members Management to only people who participate in the process.
Note on C16: Raphael Costa: Our System has permissions access and Members Management to only people who participate in the process.
Note on C20: Raphael Costa: Manually entering the quotes into the system wouldn't have such a significant impact on a specific bid. We currently have a large list of recently obtained quotes that we would like to integrate into SmartBID, independently of any specific bid at the moment.
Note on C22: Raphael Costa: The AI ​​will not recommend specific suppliers or costs. Instead, it will assist in drafting the scope of supply list by simply listing the necessary equipment, tools, and resources based only on Oceaneering Datasheets and Catalogs; AI Layer it will not address which supplier or cost price should be used. The Knowledge Base will serve solely to identify equipment and part numbers, where available.
Note on C23: Raphael Costa: We have a secure approval system with all sponsors
Note on C26: Raphael Costa: Our System has permissions access and Members Management to only people who participate in the process. Knowledge Base pages will have a dedicated access permission.
Note on C27: Raphael Costa: I believe that the commercial and sales aspect isn't covered by SmartBid.
Note on C29: Raphael Costa: Our current team of BID engineers possesses advanced knowledge of Oceaneering’s tools, which aids in the analysis and review of any AI recommendation.
Note on C30: Raphael Costa: We already have a page of "Unassigned Requests" before start working on RFQ. Every request will have a owner, reviewer and a list of approvals.

## RAM for Threats
Risk Assessment Matrix for Threats
Guideline for Impact Ratings (by Impact Type) For each Threat identified, determine the Impact Type that results in the highest Impact Rating. Subsequently, enter the Impact Rating in the Project Risk Register. | [6 empty] | Probability
[7 empty] | Highly Unlikely | Unlikely | Possible | Likely | Highly Likely
Health/Safety | Environment | Financial | Schedule | Performance | Market Reputation |  | 1 | 2 | 3 | 4 | 5
Permanent total disability with a possibility of a loss of life from an incident or occupational illness. | Severe or extensive environmental impact affecting sensitive environmental resources. Release of hazardous material beyond containment, near human populations. | Project cost increase of >15% or >$10M (whichever is less). | Significant schedule impact to critical path/major milestone(s) (=/>20% schedule extension). | Complete or material failure to achieve project objectives. | International impact with international public attention. Extensive adverse attention in international media. International policies with potentially severe impact on access to new operational areas. | 5 | Medium | Medium | High | High | High
Permanent total disability from an incident or occupational illness. | Signficant environmental impact affecting sensitive environmental resources. Extended exceedance of discharge limits. Release of hazardous material beyond containment, distant from human populations. | Project cost increase of 10% to 15% or $1M-$10M (whichever is less). | Significant schedule impact to critical path (10% to <20% schedule extension). | Failure to achieve some project objectives. | National impact. Extensive adverse attention in national media. National policies with potentially restrictive measures or impact on future operations. Mobilization of action groups. | 4 | Low | Medium | High | High | High
Major injury or health effects including days-away-from-work injuries that affect work performance in the longer term. | Limited or transient environmental impact. Minor localized impact on sensitive environmental resources. Repeated exceedance of discharge limits. Release of hazardous material beyond containment. | Project cost increase of 5% to <10% or $150K-$1M (whichever is less). | Significant schedule impact to milestone(s) (5% to <10% schedule extension). | Project objectives met but failure to achieve specifications of an element. | Considerable impact with regional client and public concern. Extensive adverse attention in local media. Slight regional political attention. Adverse stance of local government or action groups. | 3 | Low | Medium | Medium | High | High
Minor injury or health effects. Medical treatment cases, restricted-duty injuries and limited health effects that are transient or reversible (e.g., food poisoning, skin irritation). | No impact on sensitive environmental resources. Single exceedence of legal discharge limits. No hazardous material release beyond containment. | Project cost increase of 2% to <5% or $50K-$150K (whichever is less). | Minor overall schedule impact (2% to <5% schedule extension). | Partial failure to achieve specification of an element but within tolerance. | Limited impact where some local client or public concern. Some local media or political attention with potentially adverse impact for operations. | 2 | Low | Low | Medium | Medium | Medium
Potential for slight injury (including first aid cases) not affecting work performance or causing days away from work or disability. | Minor environmental impact contained within facility boundaries. No hazardous material release. | Project cost increase of <2% or <$50K (whichever is less). | Negligible schedule impact (<2% schedule extension). | No impact on project objectives. | Slight impact where Client and public awareness may exist but there is no public concern. | 1 | Low | Low | Low | Low | Medium
Guideline for Probability Ratings Note: For the identified Risk, enter the Probability Rating in the Project Risk Register.
Highly Unlikely (1) | Never occurred in the industry.
Unlikely (2) | Previously occurred in the industry.
Possible (3) | Occurs more than once per year in the industry.
Likely (4) | Occurs more than once per year in the industry and has occurred in Oceaneering.
Highly Likely (5) | Common in the industry and/or Oceaneering.
Guideline for Threat Response Plans
High (12-25) | The Threat must have a Risk Response Plan developed in order to improve the probability and/or impact to an acceptable level.
Medium1 (5-11) | The Threat may have a Risk Response Plan developed at the discretion of the Project Team in order to improve the probability and/or impact to an acceptable level.
Low (1-4) | The Threat does not require a Risk Response Plan; however the Project Team should ensure that existing controls are monitored and fully implemented to keep the risk level as low as practical.
1If the existing controls and risk mitigation do not adequately address the risk of adverse Health, Safety or Environmental effects associated with work, an adequate Risk Response Plan must be implemented before work commences or the work may not proceed, regardless of the Mitigated Risk Score.

## RAM for Opportunities
Risk Assessment Matrix for Opportunities
Guideline for Impact Ratings (by Impact Type) For each Opportunity indentified, determine the Impact Type that results in the highest Impact Rating. Subsequently, enter the Impact Rating in the Project Risk Register. |  |  | Probability of Success
|  |  | Highly Unlikely | Unlikely | Possible | Likely | Highly Likely
Financial | Schedule |  | 1 | 2 | 3 | 4 | 5
Baseline revenue increase of >15% or >$10M (whichever is more). | Significant schedule improvement to critical path/major milestone(s) (>10% net gain to planned schedule). | 5 | Medium | Medium | High | High | High
Baseline revenue increase of 10%-15% or $1M-$10M (whichever is more). | Significant schedule improvement to critical path (5%-10% net gain to planned schedule). | 4 | Low | Medium | High | High | High
Baseline revenue increase of 5%-10% or $150K-$1M (whichever is more). | Significant schedule improvement to milestone(s) (2%-5% net gain to planned schedule). | 3 | Low | Medium | Medium | High | High
Baseline revenue increase of 2%-5% or $50K-$150K (whichever is more). | Minor schedule improvement (1%-2% net gain to planned schedule). | 2 | Low | Low | Medium | Medium | Medium
Baseline revenue increase of <2% or <$50K (whichever is more). | Negligible schedule improvement (<1% net gain to planned schedule). | 1 | Low | Low | Low | Low | Medium
Guideline for Probability Ratings Note: For the indentified Opportunity, enter the Probability Rating in the Project Risk Register.
Highly Likely (5) | Common in the industry and/or Oceaneering. With suitable planning and resourcing, there is a High likelihood of the opportunity being realized
Likely (4) | Occurs more than once per year in the industry and has occurred in Oceaneering. With suitable planning and resourcing, there is a Medium to High likelihood of the opportunity being realized
Possible (3) | Occurs more than once per year in the industry/ With suitable planning and resourcing, there is a Medium likelihood of the opportunity being realized
Unlikely (2) | Previously occurred in the industry. With suitable planning and resourcing, there is a Low to Medium likelihood of the opportunity being realized
Highly Unlikely (1) | Never occurred in the industry. With suitable planning and resourcing, there is a Low likelihood of the opportunity being realized
Guideline for Opportunity Response Plans
High (12-25) | The Opportunity must have an Opportunity Response Plan to maximize value from the potential opportunity.
Medium (5-11) | The Opportunity may have an Opportunity Response Plan developed at the dsicretion of the Project Team in order to maximize the return from the potential opportunity.
Low (1-4) | The Opportunity does not require an Opportunity Response Plan; however, the Project Team should ensure that existing opportunity is monitored in case of any change in curncumstances.

## Communication Matrix (hidden)
Oceaneering Communication Matrix based on Risk Consequence
Reference: Quality DOC-COM-25-NUM Revision D
This communication protocol is to be followed based on the Residual Mitigated Consequence Level (irrespective of mitigated risk score)
|  | Event Criteria |  |  |  | Notification Method
|  | Customer Impact |  | Performance | Schedule
Consequence Level | 5 | Ø Damage to customer reputation at an international level / companywide. |  | Ø Failure occurs without warning. | Ø Potential schedule milestone extended over 30%. | Email, Phone Call
|  | Ø Impact of not being able to bid for new contracts. |  | Ø Affects / violates safe operation and / or involves non-compliance with regulations. | Ø Potential schedule slip will incur customer concessions.
|  | Ø Customer impacted downtime over 48 hrs. |  | Ø Deliverable(s) may be above 25% of budget.
Ø Equipment failure over 72 hrs.
| 4 | Ø Impact of not being awarded new contracts at a regional level. |  | Ø Deliverable(s) may need to be scrapped or above 15% of budget. | Ø Potential schedule milestone extended over 10% - 30%. | Email, Phone Call
|  | Ø Customer impacted downtime over 24 hrs. |  | Ø Deliverable(s) may be fit for purpose but may have reduced levels of primary performance. | Ø Results in delays with customer schedule.
|  | Ø Multiple contractual requirements not met. |  | Ø Equipment failure over 48 hrs.
| 3 | Ø Customer impacted downtime between 12 and 24 hrs. |  | Ø Most deliverable(s) may have to be reworked, are late, or above 10% of budget. | Ø Potential schedule milestone extended 5% - 10%. | Email
|  | Ø Concerns on performance raised by customer's corporate division. |  | Ø May have reduced level of secondary performance. | Ø Milestones require to be adjusted.
|  | Ø Impact of not being awarded new contracts at a customer, plant and/or Business Group level. |  | Ø Equipment failure over 24hrs.
| 2 | Ø Customer has issued a non-conformance or verbally expressed discontent. |  | Ø Project deliverable(s) may have to be reworked, are late, up to 10% of budget. | Ø Potential schedule milestone extended<5%.
|  | Ø Customer impacted downtime between 5and 12 hrs. |  | Ø Noticeable across departments.
Ø Equipment failure 12-24 hrs.
| 1 | Ø Customer awareness of issues may exist, but there is little concern. |  | Ø A portion of the deliverable(s) may have to be reworked, are late, or above cost. | Ø Potential minor project schedule milestone extended within scheduled contingency.
|  | Ø Issues resolved promptly through management processes. |  | Ø Equipment failure 5-12hrs.
Consequence Level |  |  | Minimum Notification Requirements |  | Notification Method
5 |  |  | CEO/COO/Legal |  | Email, Phone Call
5 ¦ 4 |  |  | SVP/VP |  | Email, Phone Call
5 ¦ 4 ¦ 3 |  |  | General Manager / Quality Director / Global Account Director / Country Manager / Quality Supervisor / Quality Manager / Operations Manager / Project Manager/ Quality Engineer / Project Engineer / Logistics Coordinator |  | Email